## Slide 1: Theory of Change
Thursday 3rd September 2015

## Slide 2: Theory of change Program of the day
9.00 – 9.15 Good morning, practical information and questions
9.15 – 9.45 Presentation: A Model for Project Work
Theory of Change
9.45 - 10.30 Group work: What is the problem?
10.30 – 10.45 Break
10.45 – 12.00 Group work: Target population
12.00 – 13.30 Lunch break
13.30 – 14.30 Effect – Outcome – Output
14.30 - 15.30 Group work: Activities - Input
15.30 – 15.45 Break
15.45 – 16.15 Group work: SMART
16.15 – 16.30 Presentation: Measuring and monitoring – indicator
RACER
16.30 – 17.00 Evaluation of the day – Learning styles?

## Slide 3: Project Work
The way we work with change in Denmark
A short review
Notes: What do you know this way of working?
I will make a very short presentation of what we mean when we are talking about Projectwork

## Slide 4: Project Work
Working with change
Starting with real problems
Everyone involved are a part of the process
Experimental work and Pilots
Evaluation – Experience and Outcomes
What works and what doesn’t?
Some elements do work
Communication and dissemination
Implementation

## Slide 5: Project example
A group of local people contacts a voluntary social organisation to discuss how to start a broad social project based on cooperation between public officials and volunteers.
The local area is characterised by:
Many older people with health problems and problems with addictions
Some residents with mental health difficulties
Some children who do not live with their parents.
Very low average income
The area is marked by abandonment and stagnancy

## Slide 6: Group work
Problem and target group
Stakeholders
Theory of change – Workshop
  Clarification of what changes are desired

## Slide 7: Organisation
Steering Group- who decides?
A Knowledge Group - who has knowledge and can give good professional advice?
Project Group
Performers of social work? – the social workers
Professional coaching, supervision and teaching?
Daily management?
Employee skills and flexibility?
NGO - volunteers?
Involvement of citizens?
Partnerships / co-creation?
A legal basis
Where do you see yourselves in this organisation?
Notes: Choose a Steering Group…….
We will come back to this question later today

## Slide 8: Considering options for learning and change along the way is critical to Project Work
Project work as a circular process
What works well?
What improvements are needed?
SWOT analysis - Strengths, Weaknesses. Opportunities and Threats?
How is the collaboration working?
Do we need to involve new partners?

## Slide 9: Collaboration in the Project Group
Developing a trusting and inclusive culture
Everyone's views must be considered seriously and discussed
How do we work with different points of view and conflicts?

## Slide 10: Project work is not a linear prcoess but a continuous cycle
Problem/Idea
Research
Implementation
Evaluation
Improvement/ opportunities
Theory of Change
Analysis

## Slide 11: Theory of Change

## Slide 12: Theory of Change
Resources
Activities
Long term Effect
Medium term Effect
Output/ Product
Short term Effect
Implementation
Planning
Money People Volunteers Etc. | Training Coaching Interventions | No. Of courses completed | More qualified social workers | Improved social work | Social change for vulnerable people
Outcome
Notes: A theory of change is not really a theory, it is in fact a process where you create clarity about what it is you want to achieve with your project.
And it is a discussion of what assumptions you have about what it is nesecerry to do if you will achieve the changes
The change for the citizens
Medfører det = causes it
Effects are quantifiable success criteria's to measure outcomes.
What are your basic assumptions?
What are the key core elements?

## Slide 13: Theory of Change – Definition
What is the problem?
  Describe the problem to be solved?

## Slide 14: Theory of Change - Definition
Who is the target population?
Describe the target group – be detailed and specific
What are the characteristics of the citizens whose lives we are accountable for improving?
Age, sex, number, problem, residence, functioning, health etc.
Choose one major target group

## Slide 15: Theory of change - Outcome
Short-term
Medium-term – Intermediate
Long-term
  A vision for the citizens in 5 years? (the target population)

## Slide 16: Theory of change - Outcome
Long term effects?
  What outcome in the long term, must we achieve in order to solve the problem?
  What targets do we need to achieve, that will lead to solving the problem in the long term? SMART goal?
Medium term effects?
  What will it take to reach the medium-term goals?
  What are the immediate products the activities lead to?
  Who will have better conditions and opportunities than before the activities were carried out?
Short term effects - Output?
  Which immediate short term results (output / product) are required to achieve medium term goals?
  What happens immediately after activity ends?
Measuring and monitoring - indicators
Notes: Intermediate – delmål
Long- term – focus on clarifying the intended ultimate social value of what you whant to achieve
Intermediate – incremental - trinvis

## Slide 17: Theory of Change - Activities
What activities must be implemented to get the desired output, which is necessary to achieve the desired results?
    Dosage
    Frequency
    Duration
Necessary competencies?
Notes: Kvalitetstjek forandringsteorien
’Hvis vi gør sådan...Så fører det til sådan… Fordi indsats x vil få person y til at reagere/agere sådan og sådan’

## Slide 18: Theory of Change – Input/Resources
What resources does it take to implement the relevant activities?
    Money?
    Employees?
    Education/competencies required?
    Project size?
    NGOs

## Slide 19: A robust Theory of Change?
Meaningful to its stakeholders
Plausible – conforming to common sense, public opinions and experts
In accordance with resource constraints
Measurable and monitorable
Operational (a useful framework for managing)

## Slide 20: Theory of Change – an example
Unge hjemløse får afklaret deres bolig- og støttebehov
The municipalities organize themselves in line with the Housing First principles.
The municipalities have developed politically approved action plans for implementation and embedding of the Housing First principle and the supported housing methods ICM, CTI and ACT
The mobile team provides local implementation support
Forum for inter-municipal networking
Rehabilitation: The citizens has regained their functional capacity to an extent that matches their own view of an independent and meaningful life
The municipalities have adequate housing to provide
Activities/deliverables
Short-term outcome
Long-term outcome
Intermediate outcome
Social inclusion
Homeless citizens are referred to appropriate housing
Kick off conference
Setting up ambassador corps
Implementation and anchoring tools
The municipalities are working methodically and rigorously with the supported housing methods.
Preparation of template for the implementation plan
The municipalities enter into external collaborations
Homeless citizens believe in own ability to maintain a home
The citizens maintains their home
The municipalities knows the current best knowledge in reducing homelessness
The homeless citizens have strengthened social and personal skills and resources
The municipalities enter into collaborations agreements and implementations plans.
The municipalities resolve the problems of the homeless citizens and prepares § 141 action plans
The homeless citizens have coordinated and coherent support
The housing and/or support needs of the homeless citizens are being clarified
Homeless citizens receive appropriate supported housing
Notes: Kyrgyzstan is not Denmark. You have other target groups and you have a total different contekst here. Sow you have to make your own theory of change. And when you make your own theoru of change you must always use al the knowledge you have. And on that background you must make teoretical and strategic adjustment to achive your goals i your theory of change. And you must also use your outcomes to learn from in your work.

## Slide 21: Theory of change – Group work
And now it's your turn to make a Theory of Change for a specific target group here in Kyrgyzstan
  The solution of social problems is always closely linked to the context they have arisen in.
Notes: 9.45 – 10.30 And before we are going to have a little break, I would like you to have a little chat with your table, about what you se as the biggest sociale problems here in Kyrgyzstan.
5 – 10 – 15 min
Kyrgyzstan is not Denmark. You have other target groups and you have a total different contekst here. Sow you have to make your own theory of change. And when you make your own theoru of change you must always use al the knowledge you have. And on that background you must make teoretical and strategic adjustment to achive your goals i your theory of change. And you must also use your outcomes to learn from in your work.

## Slide 22: Working model during the day
Individuel
Group work
All together

## Slide 23: Working model for the Group work
Example
Target group?
Reflecting individually and take notes - 5 min.
Discussing in groups - 20 min
Gathering a joint Theory of Change on the board - 20 min

## Slide 24: Break

## Slide 25: SMART
S Specific?
    Specific and unambiguous manner, focused and clearly defined. The goal or objective must be straightforward, action-oriented and clearly indicate the expected goals Who is involved? What will happen? Why is it important? How will it happen? Wh-questions can help to make the target quite specific.
M Measurable?
    A goal must be measurable. How do you know that the change has occurred? The measurement can be carried out?
A Accepted?
Is there agreement on the goal among the main players? And in the target group? Is it a good measure of what will be perceived as a success? Are there someone who will potentially work against goals being achieved?
R Realistic?
  An accepted goal is not necessarily realistic. Is it likely that the target can be achieved with the resources available? Is the goal more an expression of a dream? Or is there a clear and logical relationship between means and ends?
T Time Bound?
  When should it be measured if the goal s are reached? The deadline should be realistic and achievable.

## Slide 26: Measuring and monitoring indicators
What should be monitored?
  Indicators, frequency and by whom?
Indicators:
  Ensures the project has successful momentum
  Identifies if the project has achieved the goals
  Definition of an indicator:
  An indicator is a quantitative unit of measurement indicating whether the expected activities have been completed. A good indicator indicates a quantitative size of what the target, to be attained, is
  Indicators are used to make objectives measurable.
  RACER model - quality assurance for Indicators

## Slide 27: RACER
R Relevant?
    Is the indicator relevant to the project? Is there alignment between the indicator and the project goals?
A Accepted?
    Is the indicator generally accepted by those who have to work with it.
C Credible?
Is the indicator clear and easy to interpret? Is it credible for non-experts
E Easy?
  An Is it easy to collect data for the indicator? ? Is there alignment between cost of collection and the value of data?
R Robust?
  The indicator cannot be misused or mis-represented? Is it possible to manipulate the data?.

## Slide 28: CREAM Indicators should be:
Clear
Described in concrete operational language
Relevant
Tightly linked to essential variables that drive performance
Economical
Affordable to measure
Adequate
Sufficient for the collection of essential performance data
Monitorable
Measurable within the capacities of the organization itself, not needing external evaluators

## Slide 29: Producing a Theory of Change Quick refresher
Involve key stakeholders
Clarify the purpose (mission)
Identify the kinds and levels of knowles that will be used
Limit and specify the target population
Specify the definition of success
Manualize the program elements
Relate specific activities to incremental change in short-term outcomes
Clarify implementation challenges and indicators that will be used to manage implementation
Specify the governance and accountability systems and processes
Plan what kind of evaluation will be used

## Slide 30: Additional literature
J.Z. Kusek and R. Rist: ”Ten steps to a Results-based Monitoring and Evaluation System. Washington, DC World Bank 2004
www.dekhconsulting.com